JTC 1/SC 2  N 2913

04 July, 1997

Title:	Editors’ Report on Project JTC 1.02.15285, “An operational model for characters and glyphs”

Source:	Edwin Hart and Alan Griffee (co-editors)

Action:	For information

Distribution:	SC 2

Summary

This document describes (a) the activity since the SC 2 Plenary in Québec, and (b) the plan with status and revised schedule.  At this point, we have obtained approval of the PDTR, and are on schedule to obtain approval of the TR by the winter of 1997-1998 and publication in the spring of 1998.

The co-editors thank the National Bodies and individuals who took the time to return comments on the draft versions of TR 15285.

Activities

Here are the activities that occurred since the SC 2 Plenary Meeting in Québec, Canada, in August, 1996:

- SC 2 distributed document SC 2 N2746, working draft of TR 15285, “An operational model for characters and glyphs” to give the National Bodies the opportunity to read the draft and to submit comments to be used in the preparation of the PDTR text.

- In January 1997, the co-editors prepared a disposition of comments on SC 2 N2746 (WG 2 N1477) and prepared the PDTR 15285 document (WG 2 N1478), and submitted them to WG 2.

- At its January 1997 Meeting in Singapore, WG 2 approved the disposition of comments (WG 2 N1477) and the text for PDTR 15285 (WG 2 N1478), and forwarded the PDTR 15285 document to SC 2 for simultaneous ballot of registration and approval of the PDTR.  In February 1997, SC 2 distributed the ballot as document SC 2 N2818.

- In May 1997, the National Bodies approved the ballot.  SC 2 documented the results in document SC 2 N2879.

- In June 1997, the co-editors prepared a disposition of comments (WG 2 N1587) and revised the text of the PDTR (WG 2 N1586) and submitted them to WG 2.

- In its July 1997 Meeting in Crete, WG 2 requested that the co-editors revise the disposition of comments and the proposed text for the DTR based on the points raised at the meeting, and forward the revised documents to the SC 2 Secretariat for further processing (Resolution M33.9 in document WG 2 N1604).  As requested, the co-editors then revised the disposition of comments (WG 2 N1628, SC 2 N2901) and the text for the DTR (WG 2 N1627, SC 2 N2902) and submitted them to SC 2 for approval and for DTR processing.

- At this point, the co-editors are waiting for SC 2 to approve the disposition of comments (SC 2 N2901) and the proposed text for DTR 15285 (SC 2 N2902), and to forward the DTR text to JTC 1 for approval.

Revised Plan with Status and Schedule

Competed Activities

August, 1996:

At SC 2 Plenary Meeting

- SC 2 assigned the NP effort to WG 2.

- SC 2 appointed Edwin Hart and Alan Griffee as co-editors of the Technical Report.

- SC 2 approved concurrent registration and distribution of the PDTR for approval.

- SC 2 requested WG 2 at its January 1997 Meeting to review the proposed text for the PDTR.

September/October, 1996:

SC 2 distributed the August working draft for comments from SC 2 and SC 18.

January, 1997:

Submitted a disposition of comments and a revised document as a draft PDTR for approval to process as a PDTR.

WG 2 Meeting

WG 2 approved draft PDTR and submit to SC 2 for PDTR processing.

February, 1997:

SC 2 distributed a 3-month letter-ballot for TR registration and approval of the PDTR.

June, 1997:

The co-editors obtained results of the PDTR ballot and resolve comments.

July, 1997

WG 2 Meeting

WG 2 directed the co-editors to revise the disposition of comments on the PDTR and to revise the proposed text of the DTR as discussed in the meeting, and to forward the revisions to SC 2.

The co-editors revised the documents as requested by WG 2

Planned Activities

July, 1997

SC 2 Plenary Meeting

Vote to forward the revised draft of the Technical Report to JTC 1 for processing as a DTR.

Fall, 1997:

JTC 1 issues the DTR ballot for a 4-month ballot.

Winter, 1997-1998

Receive results of the DTR ballot.

Spring, 1998:

Prepare disposition of comments and final text of TR 15285.

Submit final text of TR to ISO/IEC for publication.