July 15, 1996

Status and Schedule for ISO/IEC Technical Report

Here is the status for this year, and the expected schedule for completing the technical report.

March, 1996

JTC 1 approved the NP.  Japan voted against approval and had two comments.

June, 1996:

Al Griffee and I submitted a new draft to SC 2/WG 2 with a request that WG 2 forward the working draft to the SC 2 Plenary Meeting with a request to start PDTR processing.  We also recommended a response to the Japanese comments on the NP ballot.  (Based on e-mail exchanges, I would expect Japan to change its vote.)  The US asked WG 2 to approve Al Griffee and I as editors and to forward the working draft to SC 2 for PDTR processing.

August, 1996:

At the WG 2 Meeting

- Vote to approve Edwin Hart and Alan Griffee as co-editors of the Technical Report and forward to SC 2 for approval.

- Vote on suggested resolution of the Japanese comments.

- Vote in SC 2/WG 2 Meeting to forward working draft of the Technical Report to SC 2 for balloting as a PDTR.

At SC 2 Plenary Meeting

- Vote to approve Edwin Hart and Alan Griffee as co-editors of the Technical Report.

- Vote to process the working draft of the Technical Report as a PDTR.

September/October, 1996:

SC 2 issues the PDTR ballot for a 3-month ballot.

December, 1996:

Vote on SC 2 PDTR ballot and decide US comments.

At X3L2 Meeting gain approval for joint meeting with X3V1 in June, 1997.

February/March, 1997:

Obtain results of the PDTR ballot.

March/April, 1997:

Draft response to comments with suggested resolution and forward to X3L2 and X3V1 for feedback.

June, 1997:

Jointly meet with X3L2, X3V1 to obtain feedback, finalize suggested resolution of comments, and submit to SC 2/WG 2.

Summer, 1997:

At the WG 2 Meeting

Vote on suggested resolution of the comments on the PDTR.

Vote in SC 2/WG 2 Meeting to forward the revised draft of the Technical Report to SC 2 for approval as a DTR.

At SC 2 Plenary Meeting

Vote to forward the revised draft of the Technical Report to JTC 1 for processing as a DTR.

Fall, 1997:

JTC 1 issues the DTR ballot for a 4-month ballot.

December, 1997:

Decide US vote and comments on the DTR.

Spring, 1998:

Receive results of the DTR ballot.

Draft resolution of comments and submit to SC 2/WG 2 for approval.

Summer, 1998:

WG 2 approves resolution of comments on the DTR and forwards to SC 2 for approval.

SC 2 Plenary approves resolution of comments.

Late Summer/Fall, 1998:

Submit final version of TR to ISO/IEC for publication.